## GL Scripts
| S. No. | Test Case | Status | Test Data | Notes
Batch 1 - GL Scripts | 1 | GL10_Script_OpennewGLAccountingPeriod_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration
| 2 | GL20_Script_ClosenewGLAccountingPeriod_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration
| 3 | GL30_Script_ManageChartofAccountValues_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration and few test steps are removed, which suppose to be part of test case. Awaiting confirmation.
| 4 | GL50_Script_ManageJournalCategories_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration
| 5 | GL90_Script_EditUnpostedJournal_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration and few test steps are removed, which suppose to be part of test case. Awaiting confirmation.
| 6 | GL110_Script_ViewJournals_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration and few test steps are removed, which suppose to be part of test case. Awaiting confirmation.
| 7 | GL120_Script_ReverseJournals_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration and few test steps are removed, which suppose to be part of test case. Awaiting confirmation.
| 8 | GL140_Script_CopyJournal_OracleInstance_21B | Working as expected | Provided by Stephanie | Script is working as expected, however still New Navigation script needed.
| 9 | GL160_Script_DeleteJournal_21B | Working as expected | Provided by Stephanie | Script is working as expected, however still New Navigation script needed.
| 10 | GL200_Script_LaunchAutoPost_21B | Pending with IBM | Provided by Stephanie | For updation of Validation steps, to change SetDelay to WaitForDuration
Batch 2 - GL Scripts | 11 | GL60_Script_CreateSingleManualJournalBatchwithAttachment_21B | Pending with IBM | Test data provided by Stephanie, Its working as expected. | Script is working as expected, however still New Navigation script needed.
| 12 | GL70_Script_CreateMultipleManualJournalBatches_21B | Pending with IBM | Test data provided by Stephanie, Its working as expected. | Script is working as expected, however still New Navigation script needed.
| 13 | GL80_Script_CreateSingleManualForeignCurrencyJournalBatch_21B | Under review, awaiting for Test Data |  | Approached Stephanie for Test data, however she is not aware of the scenario and forwarded to Sabina and Dhana. Still I tried executing using the IBM data and different combinations, but the script is failing at Step 66. Status:fail ['Create Single Manual Foreign Currency Journal Batch', 'Step 66', 'Click on Account', 'Clicked on Account', 'ClickElement', 'AccountLineCredit', 'null']
| 14 | GL100_Script_PostJournals_21B | Under review |  | Navigation issue, The script is failing at the home page and not clicking the General accounting Icon however its working fine for other scripts for me.
| 15 | GL150_Script_InquireonJournalLines_21B | Under review, awaiting for Test Data |  | Test data provided by Stepanie, however still its failling at step no 52 (IELoop)
| 16 | GL180_Script_CreateManualStatisticalJournalEntry_21B | Under review, awaiting for Test Data |  | Approached Stephanie for Test data, however she is not aware of the scenario and forwarded to Sabina and Dhana.
| 17 | GL190_Script_ReversalCriteriaSetsandAutoReversal_21B | Under review |  | Approached Stephanie for Test data, however she is not aware of the scenario and forwarded to Sabina and Dhana.
| 18 | GL220_Script_AccountMonitor_21B | Under review |  | Its failing at Step no 81 at OK Button ("Null) : Did not locate the OK Button on the browser - Test data provided by IBM
| 19 | GL240_Script_ValidateBudgetAmounts_21B | Under review
| 20 | GL250_Script_RevalueBalances_21B | Under review, awaiting for Test Data |  | Approached Stephanie for Test data, however she is not aware of the scenario and forwarded to Sabina and Dhana.
| 21 | GL260_Script_TranslateBalances_21B | Under review | Approached Stephanie, She is not aware of the scenario and forwarded the request to Dhana. | The script is failing due to security role issue. However after getting the access to the security role, and approached Stephanie for Test data, however she is not aware of the scenario and forwarded to Sabina and Dhana. Still I tried executing using the IBM data and different combinations, but the script is failing at Step 27. Status:fail ['Translate Balances', 'Step 27', 'Click on Period', 'Clicked on LedgerLink', 'SelectItemByVisibleText', 'Ledger', "Cannot locate element with text: GNB Consol\nFor documentation on this error, )
| 22 | GL280_Script_MaintainAccountingCalendar_21B | Under review | Not Needed | Executed the Test case working as expected but still need to review with Stephanie
| S. No. | Issue | Status | Resolution | Notes
| 1 | Fusion Screen layout/resolution | Reported to Subin | Subin: This is the default behaviour of fusion. The fusion screen is build on responsive design and this is the expected behaviour. To over come this issue, requested IBM provided the navigation script. | Its navigating and working fine for Ravi but failing for Rahul. When investigated issue found the s Fusion screen layout is different though the security roles are same.
| 2 | Navigation issue | Follow up | Requested new navigaton script | To overcome accessibilty issue due to security roles
| 3 | GL Batch2 Manual Scripts | Follow up |  | Email sent on Wed 16th to IBM Team, awaiting response
| 4 | GL Batch2 Scripts error | Follow up |  | Email sent on Fri 18th to IBM Team, awaiting response
| 5 | GL Security/Data Access - Request | Email send |  | Awaiting response from Stephanie - 18th June
| Test Case Name | Comments
| GL150_Script_InquireonJournalLines_21B | Executed with updated test data, however still its failing at step no 52 (IELoop)
| GL260_Script_TranslateBalances_21B | Initially the script was failing due to security role issue. However after getting the right access, still its failing at Step 27.
Status:fail
['Translate Balances', 'Step 27', 'Click on Period', 'Clicked on LedgerLink', 'SelectItemByVisibleText', 'Ledger', "Cannot locate element with text: GNB Consol\nFor documentation on this error, )
| GL220_Script_AccountMonitor_21B | Its failing at Step no 81 OK Button ("Null) : Did not locate the OK Button on the browser.
| GL100_Script_PostJournals_21B | Navigation issue, The script is failing at the home page and not clicking the General accounting Icon however its working fine for other scripts for me.

## Test Data
| S. No. | Test Case | Test Data Status
Batch 1 - GL Scripts | 1 | GL10_Script_OpennewGLAccountingPeriod_21B | Provided by Stephanie
| 2 | GL20_Script_ClosenewGLAccountingPeriod_21B | Provided by Stephanie
| 3 | GL30_Script_ManageChartofAccountValues_21B | Provided by Stephanie
| 4 | GL50_Script_ManageJournalCategories_21B | Provided by Stephanie
| 5 | GL90_Script_EditUnpostedJournal_21B | Provided by Stephanie
| 6 | GL110_Script_ViewJournals_21B | Provided by Stephanie
| 7 | GL120_Script_ReverseJournals_21B | Provided by Stephanie
| 8 | GL140_Script_CopyJournal_OracleInstance_21B | Provided by Stephanie
| 9 | GL160_Script_DeleteJournal_21B | Provided by Stephanie
| 10 | GL200_Script_LaunchAutoPost_21B | Provided by Stephanie
Batch 2 - GL Scripts | 11 | GL60_Script_CreateSingleManualJournalBatchwithAttachment_21B | Provided by Stephanie
| 12 | GL70_Script_CreateMultipleManualJournalBatches_21B | Provided by Stephanie
| 13 | GL80_Script_CreateSingleManualForeignCurrencyJournalBatch_21B | Requested to Subin
| 14 | GL100_Script_PostJournals_21B | Provided by Stephanie
| 15 | GL150_Script_InquireonJournalLines_21B | Provided by Stephanie
| 16 | GL180_Script_CreateManualStatisticalJournalEntry_21B | Requested to Subin
| 17 | GL190_Script_ReversalCriteriaSetsandAutoReversal_21B | Requested to Subin
| 18 | GL220_Script_AccountMonitor_21B | Requested to Subin
| 19 | GL240_Script_ValidateBudgetAmounts_21B | Requested to Subin
| 20 | GL250_Script_RevalueBalances_21B | Requested to Subin
| 21 | GL260_Script_TranslateBalances_21B | Requested to Subin
| 22 | GL280_Script_MaintainAccountingCalendar_21B | Provided by Stephanie

## Sheet1
Test Case Name | Comments
GL150_Script_InquireonJournalLines_21B | Executed with updated test data, however still its failling at step no 52 (IELoop)
GL260_Script_TranslateBalances_21B | Intially the script was failing due to security role issue. However after getting the right access, still its failing at Step 27. Status:fail ['Translate Balances', 'Step 27', 'Click on Period', 'Clicked on LedgerLink', 'SelectItemByVisibleText', 'Ledger', "Cannot locate element with text: GNB Consol\nFor documentation on this error, )
GL220_Script_AccountMonitor_21B | Its failing at Step no 81 OK Button ("Null) : Did not locate the OK Button on the browser.
GL100_Script_PostJournals_21B | Navigation issue, The script is failing at the home page and not clicking the General accounting Icon however its working fine for other scripts for me.
GL240_Script_ValidateBudgetAmounts_21B | Its failing at step no 38 - Status:fail ['Validate Budget Amounts', 'Step 38', 'Click on Add', 'Clicked on Add', 'ClickElement', 'Add', 'element click intercepted: Element <a href="#" onclick="this.focus();return false" class="xt8" role="button">...</a> is not clickable at point (166, 463). Other element would receive the click: <div class="AFModalGlassPane" style="width: 1903px; height: 935px; user-select: none; z-index: 30;"></div>\n (Session info: chrome=91.0.4472.106)\nBuild info: version: \'3.141.59\', revision: \'e82be7d358\', time: \'2018-11-14T08:25:53\'\nSystem info: host: \'V35ERPREP1-17\', ip: \'142.139.122.228\', os.name: \'Windows 10\', os.arch: \'amd64\', os.version: \'10.0\', java.version: \'1.8.0_281\'\nDriver info: org.openqa.selenium.chrome.ChromeDriver\nCapabilities {acceptInsecureCerts: false, browserName: chrome, browserVersion: 91.0.4472.106, chrome: {chromedriverVersion: 90.0.4430.24 (4c6d850f087da..., userDataDir: C:\\Users\\rgudugu\\AppData\\Lo...}, goog:chromeOptions: {debuggerAddress: localhost:59447}, javascriptEnabled: true, networkConnectionEnabled: false, pageLoadStrategy: normal, platform: WINDOWS, platformName: WINDOWS, proxy: Proxy(), setWindowRect: true, strictFileInteractability: false, timeouts: {implicit: 0, pageLoad: 300000, script: 30000}, unhandledPromptBehavior: dismiss and notify, webauthn:extension:largeBlob: true, webauthn:virtualAuthenticators: true}\nSession ID: ee2cf524e3177fb423e6a432494a637e'] PILLAR ... REPORT PATH